## User stories
Team project name: Domestic Repairs | [7 empty] | MoSCoW model
User story board | [7 empty] | Must have
Should have
US ID | Type | User story | Notes | Priority | Story points | Estimted time | Page/component | Could have
1 | User | I want to have a main page that contains all relevant information of how this system works, quick links, prices (if it is a part of a project) | Idealy, implement scrolling animations, use cards. Create a great UX |  |  |  | Home/Offline | Won't have
2 | User | It would be handy to have an about me page that would explain this project goals, vision, mission etc. |  |  |  |  | About
3 | User | I want a page where I can send a message for support, optionally selecting/attaching my order reference (i.e. dropdown) | If possible let a user to attach pictures/screenshots |  |  |  | ContactSupport
4 | Admin | I want to have MODERATOR PANEL where I can track all current orders, have a search by any field to find order details, get notifications in the navbar when user sends a report to support(moderator) |  |  |  |  | Moderator/Support panel
5 | Admin | I want to have a page - "Technicians", where I can: ADD a new technician user; PROMOTE basic user to technician; DELETE/LOWER(to a basic user) a technician account; or EDIT(UPDATE) a technician details |  |  |  |  | Moderator/Technicians
6 | User | I want to be able to create a new account | agree terms and conditions should be included |  |  |  | Sign up
7 | User | I want to be able to login |  |  |  |  | Sign in
8 | User | I want to be able to reset my password | this might be a pop up or a new window |  |  |  | Reset password
9 | User | I want to have a dashboard when logged in. It would contain: a quick link to "Report a new fault/Place order" button; A table of current orders and their progresses, other information |  |  |  |  | User/Dashboard
10 | User | I want to have a notification icon in the navbar which would alert me of: technician assigned to my order (with expected finish time); other order status change; order was finished; password changed (refer US 8) | same notifications should go to the email |  |  |  | User/navbar
11 | User | After order is completed I wish to rate a technician (5 star rating) |  |  |  |  | User/Dashboard
12 | User | I need a separate page to "Report a new fault" and it(form) must include: type of appliance(dropdown, with an option other); age of appliance in years(number picker, dropdown); manufacturer(dropdown, with an option other); a description of the fault; a section of personal information like phone number, email, collection/return address etc. (order details) |  |  |  |  | Report a new fault
13 | Technician | When the job is finished, I want to add a comment/summary for a customer of what have been done, what issues I faced | add note |  |  |  | Technician/Dashboard
14 | User | I want to have a single orders table where I can filter my results by STATUS; sort it by any column |  |  |  |  | User/Dashboard/Orders table
15 | User | When the order is finished I want to be able to download PDF or see a LOG of every update(with timestamps) that order had |  |  |  |  | User/Dashboard/Orders table
16 | User | I want to have my profile settings somewhere in the navbar where I could: change my password; email; billing details*; address information; name; surname; age; phone no; checkbox for email notifications etc. | * if billing will be added as a feature |  |  |  | User/navbar
17 | User | I want to delete the order if it was not yet assigned |  |  |  |  | User/Dashboard/Orders table/Cancel
18 | Technician | I want to create my own profile with my details like phone no, email etc; a list of my recent jobs completed with ratings. This should be exposed for user if he clicks on technicians profile. | The link for technitian should be in navbar ("my profile/details" or etc.) |  |  |  | Technician/Profile
19 | Technician | In dashboard, I want to have a job search list with user description provided(preferable cards based feed. Worst case - a table); a button to provide a qoute for the job (which means offer was accepted) | after a submission, a notification fires for the user - refer US 10 |  |  |  | Technician/Dashboard
20 | Admin | I want to have a quick "Statistics sections" (graphical interface) which depicts placed/in progress/done offers; separate circular satisfaction progress bar; card of under Reports with a link to answer queued questions |  |  |  |  | Moderator/Dashboard
21 | Technician | I want some important information at the top of my dashboard which is displayed in the form of a card and may include my job completion rate, the percentage of active jobs which have a technician assigned, etc. | Displayed using cards and accurate colours reflecting each component, such as red for unassigned and green for assigned jobs. |  |  |  | Technician/Dashboard
22 | Admin | I want to be able to generate unique ID's for new technicians that enable them to set up their own accounts. If they do not have a valid ID, an account should not be created. Any failed attempts should be logged. | This should be a very simple automated ID generator that uses their initials. I'd like to be able to click a link which allows me to generate these ID's without having to load an entirely new page, thus, taking me out of my dashboard. |  |  |  | Admin/Dashboard
23 | User | I want to be able to use this service from my desktop computer and my mobile phone. | Responsive web design |  |  |  | User/*
24 | User | If there is going to be an online payment feature, I'd love to have the option of subscribing for a small amount each month with the features I need opposed to paying for each job as it comes. That way, I've got support whenever I need it at a discounted price. | I should be able to see the difference between each type of subscription and also see which is the most popular option. |  |  |  | User/Payment Services
25 | User | I'd like to be able to see reviews from some of your client (technician profile) to reflect the quality of the service you provide. | I'd like this to be on the homepage of the website before I choose to sign up. |  |  |  | User/Home
26 | Admin | I want to be able to reset passwords for my technicians. This is simply for fallback purposes. If they are, for some reason, unable to reset it using their email (such as they don't receive the email) I could reset it for them. If I do this, I should be able to click an option to prompt them to change it on their first log in. | An email should be sent to the technician once this is complete. |  |  |  | Admin/Dashboard
27
28
29
30
31
32
33
34
35
36
37
38
39